# INFORME TÉCNICO

## PORTADA

| PROYECTO |  |
| --- | --- |
| Número de proyecto: | Proyecto 101183292 |
| Nombre del proyecto: | Habilidades Verdes Ahora: Habilidades Verdes Inclusivas para fortalecer la capacidad de Formación Profesional y Profesional para un futuro sostenible. |
| Acrónimo del proyecto: | GSN |

| PERIODO DE INFORME cid:image001.png@01D0B99B.7C10A740 |  |
| --- | --- |
| Número RP: | 1 |
| Duración: | del 01/01/2025 al 31/12/2025 |

## 2. PLAN DE TRABAJO, PAQUETES DE TRABAJO, ACTIVIDADES, RECURSOS Y CALENDARIO

### 2.1 Paquetes de trabajo, actividades, recursos y calendario

PAQUETES DE TRABAJO

| #### Paquete de Trabajo 1 Paquete de trabajo 1: [Nombre, por ejemplo, gestión y coordinación de proyectos] |  |  |  |
| --- | --- | --- | --- |
| Actividades Informar sobre el estado de la implementación de las actividades que debían llevarse a cabo durante el periodo de informe y explicar las desviaciones respecto al Anexo 1 del Acuerdo de Subvención. En caso de que no se haya implementado una actividad o no se haya producido un entregable, por favor explique por qué. |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name | Implemented? (Yes/No/Partially) | Justification (explain what was done and by whom; explain what was not done and why not; indicate how you intend to handle the situation and new timing; indicate if it was a one-off issue or how you intend to avoid similar issues in the future) |
| T1.1 | Kick-off meeting | Yes | COLOMBIA 2026- January-June Semester A monthly follow-up meeting led by Plan NLNO was held periodically with the assistance of Colombia from PLAN and Colombia Inclusive. In these spaces, the progress of the activities was presented and the implementation of the planned actions and the realization of key aspects in terms of monitoring indicators and communications were coordinated. Specifically, at the local level, monthly working meetings were held between PLAN and Colombia Inclusivate to coordinate the planned workshops and meetings, generating a collaborative climate that allowed the expected products of the project to be generated. |
| T1.2 | Inception and preparation | Yes | COLOMBIA. Activity completed in year 1 |
| T1.3 | Project coordination and monitoring incl. risks and opportunities | Yes | During the first half of 2026, follow-up was maintained between the local partners PLAN and Colombia Inclusivate in contractual, technical and financial aspects. The delays identified in the first year of activities were resolved through monthly financial reports and the accompaniment of a finance professional. Similarly, as a result of the assorted disbursements, adjustments were identified in the local currency for the development of the activities, which made it possible to enhance their scope. |
| T1.4 | Reporting | Yes | COLOMBIA. Activity completed in year 1 |
| T1.5 | Action learning and best practices harvesting | No | As part of the efforts to generate learning from the work process carried out in Colombia, the learning workshop led by the monitoring and evaluation area was held on June 9. This workshop was designed to be held virtually with the participating entities of the consortium and their technical work teams. The methodology proposed from Colombia was shared with the Ecuadorian team for the workshop, which had the following methodological work moments: - Identification of the main activities developed in work packages 2 and 3 during the project. - Identification of the contribution of the partner entities in the activities. - Lessons identified, learned and good practices developed in technical, financial, administrative aspects, etc. - Recommendations to enhance work in the final stage of implementation. The results of the workshop were systematized in a working document that was shared with the participating entities. |

#### Work Package 2

| Work Package 2: Develop an inclusive market‑driven curriculum on green skills for VET education |  |  |  |
| --- | --- | --- | --- |
| Activities Report on the implementation status of the activities that were to be implemented during the reporting period and explain deviations from Annex 1 of the Grant Agreement. In case an activity was not implemented or a deliverable not produced, please explain why. |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name | Implemented? (Yes/No/Partially) | Justification (explain what was done and by whom; explain what was not done and why not; indicate how you intend to handle the situation and new timing; indicate if it was a one-off issue or how you intend to avoid similar issues in the future) |
| T2.1 | Stakeholders’ needs and gap analysis on labour‑demanded green skills | Yes | COLOMBIA. Activity completed in year 1 |
| T2.2 | Market scan analysis in Colombia and Ecuador | Yes | COLOMBIA. Activity completed in year 1 |
| T2.3 | Development of an inclusive Green Skills Curriculum | Partially | During the first quarter of 2026, the Green Skills Inclusive Curriculum completed its technical adjustment with the accompaniment of the contracted consultancy and the monitoring, technical assistance team on gender of PLAN and Colombia Inclusive. This exercise made it possible to complete the production of two documents: - Facilitation Guide. It includes aspects related to conceptual, methodological and didactic approaches to teaching and 5 work modules: Module 1 Climate change and environmental problems in everyday life. Module 2 Sustainability, circular economy and community resilience. Module 3 Options for an eco-friendly lifestyle in everyday life. Module 4 Taking action communication, campaigns and activism. Module 5 Innovation and sustainable jobs for economic and labour projection. The document is annexed to: Annex 1 Key Concepts. Annex 2 Green Skills Measurement Framework - Student notebook. It includes practical exercises to consolidate knowledge and new attitudes as a result of the reflection generated during the development of the 5 work modules. The planned training process has a total of 24 hours of training and was designed to be developed in training processes articulated to the teaching of courses for short or medium term work, work with community organizations, labor insertion programs or continuous accompaniment processes. |
| T2.4 | Prototype and test the Green Skills curriculum with youth | No (not applicable in current period) | COLOMBIA. Activity completed in year 1. |

#### Work Package 3

| Work Package 3: Capacity building on inclusive innovative environmental education and environmental sustainability in VET operations |  |  |  |
| --- | --- | --- | --- |
| Activities Report on the implementation status of the activities that were to be implemented during the reporting period and explain deviations from Annex 1 of the Grant Agreement. In case an activity was not implemented or a deliverable not produced, please explain why. |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name | Implemented? (Yes/No/Partially) | Justification (explain what was done and by whom; explain what was not done and why not; indicate how you intend to handle the situation and new timing; indicate if it was a one-off issue or how you intend to avoid similar issues in the future) |
| T3.1 | Needs assessment of local VET partners | yes | COLOMBIA. Activity completed in year 1. |
| T3.2 | Training on gender equality and inclusive education | Partially | COLOMBIA. Activity completed in year 1. |
| T3.3 | Masterclass on environmental education in the EU | Yes | COLOMBIA. Activity completed in year 1. |
| T3.4 | Train‑the‑Trainer (ToT) of VET partners’ staff on innovative pedagogical methodologies for green skills | No (not applicable in current period) | COLOMBIA 2026- January-June Semester The Training of Trainers workshop in inclusive ecological skills and innovative pedagogy was held between March 17 and 20 at the facilities of the Colombia Inclusivate Foundation in Barranquilla and was facilitated by teaching staff from the foundation and CINOP. A total of 23 people participated (10 women and 13 men), teachers from Colombia Inclusivate and training centers for work and SENA in the city of the city. The workshop was divided into two moments. The first is aimed at the recognition of the project-driven green living skills methodology and practical usefulness in job training processes. The second aimed at providing participants with student-centred activating tools and methods, suitable for teaching ecological skills. During the exercises, participants were able to recognize the differentiating elements between the elements of traditional education, the 4C/ID model, challenge-based learning, projects, experience, and cases. |

#### Work Package 4

| Work Package 4: Reinforce linkage between VET and the private sector |  |  |  |
| --- | --- | --- | --- |
| Activities Report on the implementation status of the activities that were to be implemented during the reporting period and explain deviations from Annex 1 of the Grant Agreement. In case an activity was not implemented or a deliverable not produced, please explain why. |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name | Implemented? (Yes/No/Partially) | Justification (explain what was done and by whom; explain what was not done and why not; indicate how you intend to handle the situation and new timing; indicate if it was a one-off issue or how you intend to avoid similar issues in the future) |
| T4.1 | Reinforce and diversify cooperation between VET and the private sector | Not applicable in the current reporting period | COLOMBIA 2026- January-June Semester The workshop on cooperation with the private sector was held between April 14 and 17 in Barranquilla and was facilitated by CINOP staff. A total of 13 people (7 women and 6 men) from Colombia Inclusivate and Barranquilla labor intermediation agencies attached to the Public Employment Service participated. The purpose of these conferences was to improve the links of these institutions with representatives of the economic sectors, including companies, authorities and civil society organizations. To this end, the workshop was oriented to discuss the motives, principles and conditions for cooperation with the private sector, cooperation oriented to the green labour market, types of partnerships, stakeholder mapping, gender equality as a topic of common interest and quality practices. As part of this work commitment, on April 16, the discussion "Building green employment opportunities for young people" was held, which was conceived as a strategic space to advance from the analysis to action around green employment in the city. To this end, a panel discussion was set up with strategic actors from the employment and environment ecosystem such as the municipality's education secretariat, the Atlantic Regional Autonomous Corporation, the Public Employment Service Unit and the Corona Foundation. This space brought together 60 people from public and private institutions in the city of Barranquilla. |
| T4.2 | Launch the Inclusive Green Skills Curriculum in Colombia and Ecuador | Not applicable in the current reporting period. | This activity is planned to take place on August 25 in the city of Barranquilla |
| T4.3. | Facilitate recruitment and transition to jobs for young learners | Not applicable in the current reporting period | This activity is planned to be developed in the second half of 2026 |

#### Work Package 5

| Work Package 5: [Name, e.g. Project management & coordination] |  |  |  |
| --- | --- | --- | --- |
| Activities Report on the implementation status of the activities that were to be implemented during the reporting period and explain deviations from Annex 1 of the Grant Agreement. In case an activity was not implemented or a deliverable not produced, please explain why. |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name | Implemented? (Yes/No/Partially) | Justification (explain what was done and by whom; explain what was not done and why not; indicate how you intend to handle the situation and new timing; indicate if it was a one-off issue or how you intend to avoid similar issues in the future) |
| T5.1 | Definition of knowledge exchange and dissemination plan | Not applicable in the current reporting period. | COLOMBIA 2026- January-June Semester During the first half of 2026, the Plan team in Colombia participated in the discussions for the generation of the knowledge generation plan and dissemination of the curriculum. This allowed the CINOP team to carry out the expected product and determine the first activities to be developed. |
| T5.2 | Implementation of the knowledge exchange and dissemination plan | Not applicable in the current reporting period. | COLOMBIA 2026- January-June Semester The dissemination plan will begin its implementation in the second half of 2026 from the launch of the green life skills curriculum. |